## Test Summary
Module | Total Tests | P0 (Critical) | P1 (High) | P2 (Medium) | Estimated Hours | Dependencies | Status
Authentication & Authorization | 15 | 10 | 4 | 1 | 6.25 | Infrastructure | Not Started
Property Management | 25 | 8 | 10 | 7 | 10.4 | Auth, Database | Not Started
Booking & Calendar | 30 | 12 | 10 | 8 | 12.5 | Properties, Auth | Not Started
Financial & Accounting | 35 | 15 | 12 | 8 | 14.6 | Bookings, Properties | Not Started
User & Team Management | 15 | 8 | 5 | 2 | 6.25 | Auth, Email | Not Started
Task & Todo Management | 20 | 3 | 10 | 7 | 8.3 | Properties, Users | Not Started
Issue & Maintenance | 20 | 3 | 10 | 7 | 8.3 | Properties, Users | Not Started
Service Provider & Vendor | 25 | 5 | 12 | 8 | 10.4 | Auth, Documents | Not Started
Document Management | 20 | 3 | 10 | 7 | 8.3 | Auth, Storage | Not Started
Notifications & Communication | 20 | 3 | 10 | 7 | 8.3 | Auth, Email, Realtime | Not Started
Check-in/Check-out | 15 | 8 | 5 | 2 | 6.25 | Bookings, Properties | Not Started
Job & Service Request | 20 | 3 | 10 | 7 | 8.3 | Providers, Properties | Not Started
Commission & Payment | 15 | 8 | 5 | 2 | 6.25 | Bookings, Finance | Not Started
Media & Images | 15 | 3 | 8 | 4 | 6.25 | Properties, Storage | Not Started
Property Highlights | 10 | 2 | 5 | 3 | 4.2 | Properties | Not Started
Activity & Audit Logs | 10 | 5 | 3 | 2 | 4.2 | All modules | Not Started
Caching & Performance | 25 | 5 | 15 | 5 | 10.4 | Infrastructure | Not Started
Financial Reporting | 20 | 10 | 8 | 2 | 8.3 | All financial modules | Not Started

## Test Cases
Test ID | Module | Feature | Test Case | Priority | Test Type | Est. Time (min) | Preconditions | Status | Risk Level
TC-AUTH-001 | Authentication | User Registration | Validate user registration with all user types | P0 | Functional | 15 | Email service configured | Not Started | High
TC-AUTH-002 | Authentication | Login | Test login with valid/invalid credentials | P0 | Security | 10 | Users created | Not Started | High
TC-AUTH-003 | Authentication | RBAC | Verify role-based access control for all 80+ permissions | P0 | Security | 45 | All roles configured | Not Started | Critical
TC-AUTH-004 | Authentication | Session Management | Test session timeout and persistence | P0 | Security | 20 | Login functional | Not Started | High
TC-AUTH-005 | Authentication | Password Reset | Test password reset flow end-to-end | P0 | Functional | 20 | Email service | Not Started | High
TC-PROP-001 | Property Management | Create Property | Test property creation with all 9 tabs | P0 | Functional | 30 | Admin access | Not Started | High
TC-PROP-002 | Property Management | Edit Property | Test property editing with cache invalidation | P0 | Functional | 20 | Properties exist | Not Started | Medium
TC-PROP-003 | Property Management | Delete Property | Test property deletion with orphaned data handling | P0 | Functional | 15 | Test property | Not Started | High
TC-PROP-004 | Property Management | Image Gallery | Test image upload, ordering, primary selection | P0 | Functional | 25 | Property exists | Not Started | Medium
TC-PROP-005 | Property Management | PDF Export | Test property details PDF generation | P0 | Functional | 15 | Complete property data | Not Started | Low
TC-BOOK-001 | Booking | Create Booking | Test booking creation with conflict detection | P0 | Functional | 20 | Property available | Not Started | Critical
TC-BOOK-002 | Booking | Double Booking | Verify double booking prevention | P0 | Functional | 15 | Existing booking | Not Started | Critical
TC-BOOK-003 | Booking | Status Flow | Test all 8 booking status transitions | P0 | Functional | 30 | Test booking | Not Started | High
TC-BOOK-004 | Booking | Channels | Test all 8 booking channels | P1 | Functional | 40 | Channel config | Not Started | Medium
TC-BOOK-005 | Booking | Payment | Test payment status tracking | P0 | Functional | 20 | Booking exists | Not Started | High
TC-INV-001 | Invoice | Auto Generate | Test invoice generation from booking | P0 | Functional | 15 | Completed booking | Not Started | High
TC-INV-002 | Invoice | Manual Create | Test manual invoice with tax calculation | P0 | Functional | 20 | Customer exists | Not Started | High
TC-INV-003 | Invoice | Partial Payment | Test partial payment recording | P0 | Functional | 15 | Invoice exists | Not Started | High
TC-INV-004 | Invoice | PDF Generation | Test invoice PDF with email delivery | P0 | Functional | 15 | Complete invoice | Not Started | Medium
TC-INV-005 | Invoice | Status Lifecycle | Test all 6 invoice statuses | P0 | Functional | 25 | Test invoice | Not Started | Medium
TC-USER-001 | User Management | Create User | Test user creation with Supabase Auth | P0 | Functional | 20 | Admin access | Not Started | High
TC-USER-002 | User Management | Edit User | Test immediate table update on edit | P0 | Functional | 15 | User exists | Not Started | Medium
TC-USER-003 | User Management | Delete User | Test immediate table update on delete | P0 | Functional | 10 | Test user | Not Started | High
TC-USER-004 | User Management | Suspend User | Test user suspension and access revocation | P0 | Security | 20 | Active user | Not Started | High
TC-USER-005 | User Management | User Details | Test enhanced user details view | P1 | Functional | 10 | Complete user data | Not Started | Low
TC-TASK-001 | Task Management | Create Task | Test task creation and assignment | P1 | Functional | 15 | Property, assignee | Not Started | Low
TC-TASK-002 | Task Management | Task Workflow | Test task status transitions | P1 | Functional | 20 | Task exists | Not Started | Low
TC-TASK-003 | Task Management | Checklist | Test checklist functionality | P2 | Functional | 15 | Task with checklist | Not Started | Low
TC-TASK-004 | Task Management | Due Dates | Test due date alerts and overdue status | P1 | Functional | 15 | Tasks with dates | Not Started | Medium
TC-TASK-005 | Task Management | Bulk Operations | Test bulk task operations | P2 | Functional | 15 | Multiple tasks | Not Started | Low
TC-COI-001 | COI Management | Upload COI | Test COI document upload | P0 | Functional | 15 | Provider exists | Not Started | High
TC-COI-002 | COI Management | Expiration Alerts | Test 30/15/7/0 day expiration alerts | P0 | Functional | 30 | COI with dates | Not Started | High
TC-COI-003 | COI Management | Coverage Types | Test all 6 coverage types | P1 | Functional | 20 | COI documents | Not Started | Medium
TC-COI-004 | COI Management | Building Requirements | Test building COI requirements | P1 | Functional | 20 | Building config | Not Started | Medium
TC-COI-005 | COI Management | Access Auth | Test access authorization workflow | P1 | Functional | 25 | Provider, property | Not Started | Medium
TC-CHECKIN-001 | Check-in/Out | Digital Check-in | Test check-in with photos and signature | P0 | Functional | 30 | Active booking | Not Started | High
TC-CHECKIN-002 | Check-in/Out | PDF Generation | Test check-in PDF with all components | P0 | Functional | 15 | Complete check-in | Not Started | Medium
TC-CHECKIN-003 | Check-in/Out | Check-out | Test check-out and comparison | P0 | Functional | 30 | Check-in exists | Not Started | High
TC-CHECKIN-004 | Check-in/Out | Checklist | Test checklist templates | P1 | Functional | 20 | Template exists | Not Started | Low
TC-CHECKIN-005 | Check-in/Out | Damage Report | Test damage documentation | P0 | Functional | 20 | Check-in/out data | Not Started | High
TC-COMM-001 | Commission | Calculation | Test commission calculation accuracy | P0 | Financial | 20 | Completed bookings | Not Started | Critical
TC-COMM-002 | Commission | Payment | Test commission payment workflow | P0 | Financial | 20 | Calculated commission | Not Started | High
TC-COMM-003 | Commission | Analytics | Test commission analytics dashboard | P1 | Functional | 20 | Commission data | Not Started | Low
TC-COMM-004 | Commission | Bulk Processing | Test bulk commission approval | P1 | Functional | 15 | Multiple commissions | Not Started | Medium
TC-COMM-005 | Commission | Reconciliation | Test commission reconciliation | P0 | Financial | 25 | Payment records | Not Started | High
TC-CACHE-001 | Performance | React Query | Test memory cache behavior | P1 | Performance | 20 | Application running | Not Started | Medium
TC-CACHE-002 | Performance | Service Worker | Test offline functionality | P1 | Performance | 25 | Browser support | Not Started | High
TC-CACHE-003 | Performance | Real-time Sync | Test cache invalidation on updates | P1 | Functional | 20 | Multiple tabs | Not Started | High
TC-CACHE-004 | Performance | Load Time | Test initial page load < 3s | P0 | Performance | 15 | Clear cache | Not Started | High
TC-CACHE-005 | Performance | Large Dataset | Test with 1000+ records | P1 | Performance | 30 | Test data | Not Started | Medium

## Execution Schedule
Week | Phase | Modules | Test Count | Resources | Priority Focus
Week 1 | Setup & Auth | Environment Setup | 0 | 1 DevOps | Infrastructure
Week 1 | Setup & Auth | Authentication & Authorization | 15 | 2 Testers | P0 - Critical
Week 1 | Core Features | Property Management | 25 | 3 Testers | P0 - Critical
Week 1 | Core Features | Booking Management | 30 | 3 Testers | P0 - Critical
Week 1 | Core Features | User Management | 15 | 2 Testers | P0 - Critical
Week 2 | Financial | Invoices | 35 | 2 Testers | P0 - Critical
Week 2 | Financial | Expenses & Financial Reports | 20 | 2 Testers | P0 & P1
Week 2 | Operations | Tasks & Issues | 40 | 3 Testers | P1 - High
Week 2 | Operations | Providers & COI | 45 | 3 Testers | P1 - High
Week 2 | Operations | Documents | 20 | 2 Testers | P1 - High
Week 3 | Advanced Features | Check-in/Out | 35 | 3 Testers | P1 & P2
Week 3 | Advanced Features | Notifications & Jobs | 35 | 3 Testers | P1 & P2
Week 3 | Integration | Email & Storage | 30 | 2 Testers | P1 - High
Week 3 | Integration | Real-time & Cache | 25 | 2 Testers | P1 - High
Week 4 | Performance | Load Testing | 30 | 2 Testers + Tools | P0 - Critical
Week 4 | Security | Security Testing | 30 | 1 Security Expert | P0 - Critical
Week 4 | UAT Prep | Bug Fixes | 0 | 2 Developers | All Priorities
Week 4 | UAT | User Acceptance | 50 | 5 End Users | Business Critical

## Test Environments
Environment | Purpose | Database | Users Required | Data Requirements | Tools | Access Level
Development | Initial testing, debugging | Supabase Dev | 10 test users | Basic test data | Browser DevTools | Developer
Staging | Integration testing | Supabase Staging | 50 test users | Comprehensive test data | Postman, Browser Stack | QA Team
Production Mirror | Pre-production validation | Production Clone | Production-like data | Anonymized production data | Monitoring tools | QA + DevOps
Performance | Load and stress testing | High-capacity instance | 1000+ test users | Large datasets | JMeter, K6 | Performance Team
Security | Vulnerability testing | Isolated instance | Various privilege levels | Attack vectors | OWASP ZAP, Burp Suite | Security Team

## Bug Severity
Severity | Description | Response Time | Resolution Time | Examples | Escalation
S1 - Critical | System crash, data loss, security breach, complete feature failure | Immediate | 4 hours | Login failure, payment processing error, data deletion bug | CTO + Dev Lead
S2 - High | Major feature broken, significant performance issue, data corruption risk | 4 hours | 24 hours | Search not working, PDF generation failure, cache corruption | Dev Lead
S3 - Medium | Feature partially broken, workaround available, moderate UX issue | 24 hours | 3 days | Sorting issue, minor calculation error, UI alignment | QA Lead
S4 - Low | Minor issue, cosmetic, slight inconvenience, edge case | 72 hours | 1 week | Typo, color inconsistency, tooltip missing | Developer
S5 - Enhancement | Feature request, nice to have, improvement suggestion | Next release | Future release | New report type, additional filter, UI enhancement | Product Owner

## Test Data
Data Type | Minimum Required | Recommended | Variations Needed | Special Cases | Generation Method
Users | 20 | 50 | 4 roles, active/inactive, suspended | Admin user, suspended user, deleted user | Script + Manual
Properties | 50 | 100 | All types, various statuses, with/without images | No amenities, max amenities, archived | Script + Images
Bookings | 200 | 500 | All channels, all statuses, various dates | Overlapping, cancelled, extended stay | Script
Invoices | 150 | 300 | All statuses, partial payments, various amounts | Overdue, refunded, disputed | Script from bookings
Tasks | 100 | 250 | All priorities, all statuses, with checklists | Overdue, recurring, delegated | Script
Providers | 30 | 50 | Service and utility types, with ratings | Preferred, emergency contact | Manual + Import
Documents | 100 | 200 | All categories, various file types | Expired, large files, restricted | Upload samples
COIs | 20 | 40 | Expired, expiring, valid | Missing coverage, expired | Manual upload
Check-ins | 50 | 100 | Complete, partial, with issues | Damage reported, signature missing | Manual process
Commissions | 100 | 200 | Calculated, paid, pending | Disputed, adjusted, bulk processed | Calculate from bookings

## Security Tests
Test ID | Category | Test Case | Method | Expected Result | Tools
SEC-001 | SQL Injection | Test SQL injection in all input fields | Input: ' OR '1'='1; DROP TABLE users; | Input sanitized, query safe | SQLMap, Manual
SEC-002 | XSS | Test XSS in text inputs and rich text | Input: <script>alert("XSS")</script> | Scripts not executed, encoded | Manual, XSS Scanner
SEC-003 | CSRF | Test CSRF token validation | Modify/remove CSRF tokens | Request rejected | Burp Suite
SEC-004 | Authentication | Test brute force protection | Automated login attempts | Account locked after X attempts | Hydra, Custom script
SEC-005 | Authorization | Test privilege escalation attempts | Modify user role in requests | Access denied, role unchanged | Burp Suite, Manual
SEC-006 | Session | Test session hijacking prevention | Token manipulation | Session invalid, logout | Manual, Wireshark
SEC-007 | File Upload | Test malicious file upload prevention | Upload .exe, .php, oversized files | Upload rejected | Manual upload tests
SEC-008 | API Security | Test API authentication and authorization | Access without auth tokens | Unauthorized error | Postman, cURL
SEC-009 | Data Exposure | Test for sensitive data in responses | Check API responses, browser storage | No sensitive data exposed | Browser DevTools, Proxy
SEC-010 | Rate Limiting | Test rate limiting on all endpoints | Rapid API calls | Rate limit enforced | Apache Bench, Custom scripts

## Performance Metrics
Metric | Target | Acceptable | Test Method | Frequency | Notes
Page Load Time | < 3 seconds | < 5 seconds | Lighthouse, GTmetrix | Every deployment | Test on 3G connection
Time to Interactive | < 5 seconds | < 8 seconds | Chrome DevTools | Every deployment | Include all resources
API Response Time | < 200ms | < 500ms | API monitoring | Continuous | Average of all endpoints
Database Query Time | < 100ms | < 300ms | Database profiler | Weekly | Complex queries only
File Upload Time | < 2s per MB | < 3s per MB | Network monitoring | On changes | Test with images
PDF Generation | < 5 seconds | < 8 seconds | Timer in code | On changes | Include all sections
Search Response | < 500ms | < 1 second | Search with 1000+ records | Weekly | Full-text search
Login Time | < 1 second | < 2 seconds | Automated login test | Daily | Include 2FA if enabled
Data Export Time | < 10 seconds | < 20 seconds | 1000 record export | Weekly | CSV and PDF formats
Cache Hit Rate | > 80% | > 60% | Cache analytics | Continuous | Monitor all cache layers

## Regression Suite
Module | Feature | Test Cases | Priority | Automation
Authentication | Login/Logout | Basic login, Remember me, Logout | P0 | Yes
Authentication | Permissions | Role verification for key features | P0 | Yes
Properties | CRUD | Create, Edit, View, Delete | P0 | Yes
Properties | Search | Basic search, Filters | P1 | Yes
Bookings | Create | Basic booking, Conflict check | P0 | Yes
Bookings | Status | Status transitions | P0 | Partial
Invoices | Generate | From booking, Manual | P0 | Yes
Invoices | Payment | Record payment, Status update | P0 | Yes
Users | Management | Create, Edit, Suspend | P0 | Yes
Users | Profile | View, Edit own profile | P1 | Yes
Notifications | Delivery | In-app notifications | P1 | Partial
Check-in/Out | Process | Basic check-in/out | P0 | No
Reports | Generation | Key financial reports | P1 | Partial
Cache | Invalidation | Update reflects immediately | P0 | Yes
Performance | Load Time | Page loads within limits | P0 | Yes

## Exit Criteria
Phase | Pass Criteria | Fail Criteria | Sign-off Required | Documentation | Rollback Plan
Unit Testing | 100% code coverage for critical paths | Coverage < 70% | Dev Lead | Unit test reports | Fix and retest
Integration Testing | All APIs return correct data | API failures > 5% | Tech Lead | API test results | Fix integration issues
System Testing | 95% test cases passed | P0 bugs exist | QA Lead | Test execution report | Hotfix or rollback
Performance Testing | All metrics within acceptable range | Performance degradation > 20% | DevOps Lead | Performance report | Performance tuning
Security Testing | No critical vulnerabilities | Critical vulnerabilities found | Security Lead | Security audit report | Security patches
UAT | 90% user scenarios successful | User rejection > 20% | Product Owner | UAT feedback | Address feedback
Production Release | All P0 and P1 bugs fixed | Any P0 bugs remain | CTO + Product Owner | Release notes | Emergency rollback